## Sheet1
WBS | Task Name | Duration | Baseline | Actual Work | Estimated Cost per Hour | Total Estimated Cost | Total Actual Cost | Variance | Duration Variance | Duration Percent Complete | Work Variance | Work Percent Complete | Cost Variance | Status
1.1.1.1 | Gather Required Documents | 3 days | 10 hrs | 10 hrs | 50 | 500 | 500 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.1.1.2 | Complete Permit Applications | 2 days | 5 hrs | 6 hrs | 60 | 300 | 360 | 60 | 1 | 120% | 1 | 120% | 60 | In Progress
1.1.1.3 | Submit Permit Applications | 5 days | 8 hrs | 8 hrs | 55 | 440 | 440 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.1.1.4 | Post Construction Permit | 1 day | 3 hrs | 4 hrs | 45 | 135 | 180 | 45 | 1 | 133.3% | 1 | 133.3% | 45 | In Progress
1.1.2.1 | Initial Site Survey | 7 days | 26 hrs | 32 hrs | 70 | 1820 | 2240 | 420 | 6 | 123.1% | 6 | 123.1% | 420 | In Progress
1.1.2.2 | Develop Site Plan | 4 days | 18 hrs | 18 hrs | 65 | 1170 | 1170 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.1.2.3 | Approve Site Plan | 3 days | 3 hrs | 6 hrs | 55 | 165 | 330 | 165 | 3 | 200% | 3 | 200% | 165 | In Progress
1.2.1.1 | Dig Foundation Footers | 2 days | 16 hrs | 25 hrs | 75 | 1200 | 1875 | 675 | 9 | 156.2% | 9 | 156.2% | 675 | In Progress
1.2.1.2 | Pour Foundation Footers | 4 days | 7 hrs | 7 hrs | 80 | 560 | 560 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.1.3 | Inspect Foundation Footers | 2 days | 2 hrs | 2 hrs | 50 | 100 | 100 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.1.4 | Build Foundation Wall | 9 days | 72 hrs | 72 hrs | 85 | 6120 | 6120 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.1.5 | Inspect Foundation Wall | 2 days | 3 hrs | 4 hrs | 60 | 180 | 240 | 60 | 1 | 133.3% | 1 | 133.3% | 60 | In Progress
1.2.2.1 | Order Framing Materials | 1 day | 8 hrs | 8 hrs | 70 | 560 | 560 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.2.2 | Frame Floor & Walls & Roof | 14 days | 112 hrs | 114 hrs | 90 | 10080 | 10260 | 180 | 2 | 101.8% | 2 | 101.8% | 180 | In Progress
1.2.2.3 | Install Widows & Doors | 3 days | 20 hrs | 20 hrs | 65 | 1300 | 1300 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.2.4 | Perform Framing Inspection | 2 days | 3 hrs | 3 hrs | 55 | 165 | 165 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.3.1 | Perform HVAC Rough In | 4 days | 32 hrs | 32 hrs | 80 | 2560 | 2560 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.3.2 | Perform Plumbing Rough In | 4 days | 32 hrs | 34 hrs | 85 | 2720 | 2890 | 170 | 2 | 106.2% | 2 | 106.2% | 170 | In Progress
1.2.3.3 | Perform Electrical Rough In | 5 days | 40 hrs | 44 hrs | 75 | 3000 | 3300 | 300 | 4 | 110% | 4 | 110% | 300 | In Progress
1.2.3.4.1 | Insect Rough In by PM | 1 day | 3 hrs | 3 hrs | 50 | 150 | 150 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.3.4.2 | Inspect Rough In by Code Officer | 2 days | 4 hrs | 4 hrs | 60 | 240 | 240 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.3.5.1 | Install Wall & Floor Insulation | 4 days | 32 hrs | 34 hrs | 65 | 2080 | 2210 | 130 | 2 | 106.2% | 2 | 106.2% | 130 | In Progress
1.2.3.5.2 | Perform Insulation Inspection | 2 days | 3 hrs | 4 hrs | 55 | 165 | 220 | 55 | 1 | 133.3% | 1 | 133.3% | 55 | In Progress
1.2.4.1 | Apply Foundation Siding | 6 days | 48 hrs | 48 hrs | 70 | 3360 | 3360 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.4.2 | Lay Brick & Rock Siding | 12 days | 96 hrs | 96 hrs | 95 | 9120 | 9120 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.4.3 | Install Exterior Trim | 4 days | 24 hrs | 24 hrs | 65 | 1560 | 1560 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.4.4 | Inspect Exterior Siding & Trim | 2 days | 3 hrs | 3 hrs | 50 | 150 | 150 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.4.5 | Paint Exterior Trim | 6 days | 38 hrs | 38 hrs | 70 | 2660 | 2660 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.5.1.1 | Hang Interior Drywall | 4 days | 32 hrs | 34 hrs | 75 | 2400 | 2550 | 150 | 2 | 106.2% | 2 | 106.2% | 150 | In Progress
1.2.5.1.2 | Finish Interior Drywall | 12 days | 65 hrs | 45 hrs | 60 | 3900 | 2700 | -1200 | -20 | 69.23% | -20 | 69.23% | -1200 | In Progress
1.2.6.2.1 | Pour concrete driveway | 4 days | 8 hrs | 8 hrs | 80 | 640 | 640 | 0 | 0 | 100% | 0 | 100% | 0 | Completed
1.2.6.3.1 | Build Exterior Deck | 4 days | 32 hrs | 6 hrs | 85 | 2720 | 510 | -2210 | -26 | 18.75% | -26 | 18.75% | -2210 | In Progress