## Risk Register
RISK REGISTER
| RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER
| Brief Summary | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible?
| Oil Platform Instability due to age | Negative | 2 | 4 | 8 | Find asotherr used platform | Project Manager | PROBABILITY | 5 | 5 | 10 | 15 | 20 | 25
| Material/Steel shortage for hyper tunne4l construction | Unintended | 4 | 3 | 12 | Obtain steel from Canada or Mexico | Project Sponsor |  | 4 | 4 | 8 | 12 | 16 | 20
| Tesla backs out of project in construction of hyper tunnel | Unintended | 2 | 2 | 4 | backup competitor: SpaceX or Boeing | Project Sponsor |  | 3 | 3 | 6 | 9 | 12 | 15
| Access denied to countries for plant/seed allocation | Unintended | 2 | 4 | 8 | Seek assistance from one of their neighboring allies | Project Manager |  | 2 | 2 | 4 | 6 | 8 | 10
| Access denied to countries bordering seas for water life | Unintended | 3 | 2 | 6 | Seek assistance from one of their neighboring allies | Project Manager |  | 1 | 1 | 2 | 3 | 4 | 5
| Not enough qualified American scientists | Negative | 4 | 4 | 16 | Seek emploployees from India, Russia, and Japan | Project Sponsor |  |  | 1 | 2 | 3 | 4 | 5
| Underground blockage of underwater tunnel constructiuon | Intended | 5 | 5 | 25 | Reroute temporarily above sea level | Project Manager |  | IMPACT
| Cryogenic cell storage incompatible with water based sites | Unintended | 3 | 4 | 12 | Secondary process option: Vitrification | Project Sponsor
| Impending catastropphic event happeniong unexpectedly before completion of all projects | Negative | 5 | 5 | 25 | Life possibly ends | Project Sponsor
| Government funds become unapproved to fiinsh any site, tunnel, or project | Negative | 2 | 2 | 4 | Consider private fund borrowing or allocation from crypto-related based corporations | Project Manager
Note on A1: Gordon Elliott Williams: This was partially borrowed from LucidCharts.com

## BUDGET
| Project Name | Saving Terra | Course Project: Projected Budget
| Project Manager | Gordon Elliott Williams
| Date | 2021-06-06
| Class | BUS530 - Project Management
| Version | 2.0
BUDGET FOR PRIMARY SITE
Task No. | Task Description | Estimated Cost(s)
Level 1 - Primary
1.1 | Primary Site Appropriation - Underground | 2000000 |  | Items | Estimated Costs
1.2 | Federal Legal Approvals, Taxes, Regulations, etc. | 500000 |  | Cell Harvesting | 40000000
1.3 | State Legal Approvals, Taxes, Regulations, etc. | 480000 |  | Concrete Flatwork | 750000
1.4 | Local Legal Approvals, Taxes, Regulations, etc. | 300000 |  | Cryogenics and Cryopreservation | 12000000
1.5 | Primary Contractor | 6000000 |  | Electrical and Cooling Systems | 4500000
| Subtotal | 9280000 |  | Electrical and Fiberoptic Wiring | 1750000
| Level 2 - Subcontractors |  |  | Excavation and Soil Removal | 3000000
1.2.1 | Security Systems | 2000000 |  | Federal Legal Approvals, Taxes, Regulations, etc. | 500000
1.2.2 | HVAC | 2000000 |  | Fire Systems | 4200000
1.2.3 | Excavation and Soil Removal | 3000000 |  | Foundations | 3000000
1.2.4 | Tree Removal and Replantation (per State Agreement) | 480000 |  | Gene Therapy | 65000000
1.2.5 | Electrical and Fiberoptic Wiring | 1750000 |  | HVAC | 2000000
1.2.6 | Plumbing | 4500000 |  | Interior Modeling (Security Level Delta-5 Black Clearance only) | 5000000
1.2.7 | Technology, Internet | 230000 |  | Local Legal Approvals, Taxes, Regulations, etc. | 300000
1.2.8 | Foundations | 3000000 |  | Microtrenching | 2000000
1.2.9 | Concrete Flatwork | 750000 |  | Plumbing | 4500000
1.2.A | Roofing | 1000800 |  | Primary Contractor | 6000000
1.2.B | Interior Modeling (Security Level Delta-5 Black Clearance only) | 5000000 |  | Primary Site Appropriation - Underground | 2000000
1.2.C | Microtrenching | 2000000 |  | Roofing | 1000800
| Subtotal | 25710800 |  | Security Systems | 2000000
| Level 3 - Secured Interior Projects |  |  | State Legal Approvals, Taxes, Regulations, etc. | 480000
1.3.1 | Cryogenics and Cryopreservation | 12000000 |  | Subtotal | 160690800
1.3.2 | Electrical and Cooling Systems | 4500000 |  | Technology, Internet | 230000
1.3.3 | Fire Systems | 4200000 |  | Tree Removal and Replantation (per State Agreement) | 480000
1.3.4 | Cell Harvesting | 40000000 |  | Grand Total | 321381600
1.3.5 | Gene Therapy | 65000000
| Subtotal | 125700000
| Totals for Site A |  | 160690800
BUDGET FOR OFFSHORE SITE
Task No. | Task Description | Estimated Cost(s)
Level 1 - Primary
1.1 | Primary Site Appropriation - Offshore | 650000000
1.2 | Federal Legal Approvals, Taxes, Regulations, etc. | 500000
1.3 | Offshore/Seafaring Legal Approvals, Taxes, Regulations, etc. | 500000
1.4 | National Marine Fisheries Service | 250000
1.5 | National Oceanic and Atmospheric Administration | 425000
| Subtotal | 651675000
Level 2 - Subcontractors & Other Legal Entities
1.2.1 | Fishery Management Plan for Regulating Offfshore Aquaculture | 1000000
1.2.2 | Gulf of Mexico Fishery Management Council | 1000000
1.2.3 | Magnuson-Stevens Fishery Conversation and Management Act | 1000000
1.2.4 | National Aquaculture Policy | 1000000
1.2.5 | Federal Energy Regulatory Commission | 1000000
1.2.6 | Bureau of Land Management | 1000000
1.2.7 | Bureau of Ocean Energy Management | 1000000
1.2.8 | Bureau of Safety and Environmental Enforcement | 1000000
1.2.9 | Environmental Protection Agency | 1000000
1.2.A | Pipeline and Hazardous Materials Safety Administration | 5000000
1.2.B | Subcontractor Refitment of Site | 250000000
| Subtotal | 264000000
Level 3 - Security ans Safety
1.3.1 | Cryogenics and Cryopreservation | 12000000
1.3.2 | Electrical and Cooling Systems | 4500000
1.3.3 | Fire Systems | 4200000
1.3.4 | Cell Harvesting | 40000000
1.3.5 | Gene Therapy | 65000000
| Subtotal | 125700000
| Totals for Site B |  | 1041375000
BUDGET FOR EMERGENCY HYPERLOOP |  |  |  | Items | Estimated Costs
Task No. | Task Description | Estimated Cost(s) |  | American Steel Corporation | 1000000000
| Level 1 - Primary |  |  | Boeing | 658000000
1.1 | Federal EPA Approvals | 650000000 |  | Cell Harvesting | 40000000
1.2 | Federal Legal Approvals, Taxes, Regulations, etc. | 500000 |  | Cryogenics and Cryopreservation | 12000000
1.3 | State Legal Approvals, Taxes, Regulations, etc. | 480000 |  | Electrical and Cooling Systems | 4500000
1.4 | Local Legal Approvals, Taxes, Regulations, etc. | 300000 |  | Excavation (Security Level Delta-5 Black Clearance only) | 17000000
1.5 | Primary Contractor | 6000000 |  | Federal Energy Regulatory Commission | 1000000
| Subtotal | 657280000 |  | Federal EPA Approvals | 650000000
| Level 2 - Subcontractors |  |  | Federal Legal Approvals, Taxes, Regulations, etc. | 500000
1.2.1 | Tubing (Security Level Delta-5 Black Clearance only) | 130000000 |  | Fire Systems | 4200000
1.2.2 | Excavation (Security Level Delta-5 Black Clearance only) | 17000000 |  | Gene Therapy | 65000000
1.2.3 | Underwater Excavation | 45000000 |  | Hyperloop Transportation Technologies | 650000000
1.2.4 | Hyperloop Transportation Technologies | 650000000 |  | Local Legal Approvals, Taxes, Regulations, etc. | 300000
1.2.5 | Federal Energy Regulatory Commission | 1000000 |  | Primary Contractor | 6000000
1.2.6 | SpaceX | 820196000 |  | SpaceX | 820196000
1.2.7 | Tesla | 0 |  | State Legal Approvals, Taxes, Regulations, etc. | 480000
1.2.8 | Virgin Hyperloop One | 765000000 |  | Tesla | 0
1.2.9 | Toray Advanced Composites | 423000000 |  | Toray Advanced Composites | 423000000
1.2.A | Boeing | 658000000 |  | Tubing (Security Level Delta-5 Black Clearance only) | 130000000
1.2.B | American Steel Corporation | 1000000000 |  | Underwater Excavation | 45000000
| Subtotal | 4509196000 |  | Virgin Hyperloop One | 765000000
| Level 3 - Security ans Safety |  |  | Grand Total | 10584352000
1.3.1 | Cryogenics and Cryopreservation | 12000000
1.3.2 | Electrical and Cooling Systems | 4500000
1.3.3 | Fire Systems | 4200000
1.3.4 | Cell Harvesting | 40000000
1.3.5 | Gene Therapy | 65000000
| Subtotal | 125700000
| Totals for Site B |  | 5292176000

## WBS
| Project Name | Saving Terra
| Project Manager | Gordon Elliott Williams
| Date | 2021-05-28
| Class | BUS530 - Project Management
| Version | 1.0
WORK BREAKDOWN STRUCTURE
Task No. | Task Description | Task Owner | Task Status | Cost | Start Date | Estimated Completion | Finish Date
1.0 | Initiation & Planning Phase
Level 1 - Fund Allocation & Site Approval
1.1 | Primary Site Appropriation - Underground | Project Manager | In Progress | $2 million | 2021-07-01 | Ongoing
1.2 | Secondary Site Appropriation - Offshore | Project Manager | In Progress | $100,0000 - $250,000 | 2021-07-01 | Ongoing
1.3 | Congressional Approval for Fund Allocation | Project Manager | In Progress | $50 billion (military budget) | 2021-06-30 | Ongoing
1.4 | Underground Engineering & Excavation | Project Manager | In Progress | $50 billion (military budget) | 2021-08-01 | Ongoing
1.5 | Offshore Engineering & Builders | Project Manager | In Progress | $100,0000 - $250,000 | 2021-08-01 | Ongoing
Level 2 - Communication & Transportation
1.2.1 | Hyperloop Interconnectivity | Elon Musk | Assigned | $20 billion | 2022-12-01 | 1 year
1.2.2 | Underground Fiberoptics/Microtrenching | Teraspan | Assigned | $35/linear foot | 2022-12-01 | 1 year
Level 3 - Solicitation of Hiring Body
1.3.1 | Project Manager's Assistant | Project Manager | Assigned | Unknown | Summer 2021 | Ongoing
1.3.2 | Project Sponsor | Project Manager | Assigned | Unknown | Summer 2021 | Ongoing
1.3.3 | Randstad | Project Sponsor | Assigned | Unknown | Summer 2021 | Ongoing
1.3.4 | ResearchGate | Project Sponsor | Assigned | Unknown | Summer 2021 | Ongoing
1.3.5 | Kolabtree | Project Sponsor | Assigned | Unknown | Summer 2021 | Ongoing
2.0 | Execution Phase
Level 1
2.1 | Primary & Secondary Site Allocation | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.2 | Primary Site - Underground - Excavation | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.3 | Secondary Site - Abandoned Offshore Oil Rig - Refitment | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.4 | OSHA - Occupational Safety & Health Administration | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.5 | Alcor - Cryogenic Freezing, Preservation, & Storage | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
Level 2
2.2.1 | Lockheed Martin - Electrical Engineering | Project Sponsor | Assigned | Unknown | Spring 2022 | Ongoing
2.2.2 | Baldridge & Associates - Structural Engineering | Project Sponsor | Unassigned | Unknown | Spring 2022 | Ongoing
Level 3
2.3.1 | Roto Rooters - Plumbing Company | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
2.3.2 | Ameriquai - Meals Ready To Eat | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
2.3.3 | Blacks Water Conditioning - Water Purification | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.0 | Performance & Monitoring Phase
Level 1
3.1 | Completion of Facilities for Storage | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.2 | International Approval for Scientists to Enter Regions | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.3 | Primary backup of all seedlings of the Doomsday Vault | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.4 | Secondary backup of all seedlings of the Doomsday Vault | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.5 | Record Coordiation of all Sites & Doomsday Vault | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
Level 2
3.2.1 | Biologists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.2.2 | Agronomists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
Level 3
3.3.1 | Botanists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.3.2 | Cytologists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.3.3 | Marine Biologists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing