## Task List
| Project Name | Saving Terra
| Project Manager | Gordon Elliott Williams
| Date | 2021-05-28
| Class | BUS530 - Project Management
| Version | 1.0
WORK BREAKDOWN STRUCTURE
Task No. | Task Description | Task Owner | Task Status | Cost | Start Date | Estimated Completion | Finish Date
1.0 | Initiation & Planning Phase
Level 1 - Fund Allocation & Site Approval
1.1 | Primary Site Appropriation - Underground | Project Manager | In Progress | $2 million | 2021-07-01 | Ongoing
1.2 | Secondary Site Appropriation - Offshore | Project Manager | In Progress | $100,0000 - $250,000 | 2021-07-01 | Ongoing
1.3 | Congressional Approval for Fund Allocation | Project Manager | In Progress | $50 billion (military budget) | 2021-06-30 | Ongoing
1.4 | Underground Engineering & Excavation | Project Manager | In Progress | $50 billion (military budget) | 2021-08-01 | Ongoing
1.5 | Offshore Engineering & Builders | Project Manager | In Progress | $100,0000 - $250,000 | 2021-08-01 | Ongoing
Level 2 - Communication & Transportation
1.2.1 | Hyperloop Interconnectivity | Elon Musk | Assigned | $20 billion | 2022-12-01 | 1 year
1.2.2 | Underground Fiberoptics/Microtrenching | Teraspan | Assigned | $35/linear foot | 2022-12-01 | 1 year
Level 3 - Solicitation of Hiring Body
1.3.1 | Project Manager's Assistant | Project Manager | Assigned | Unknown | Summer 2021 | Ongoing
1.3.2 | Project Sponsor | Project Manager | Assigned | Unknown | Summer 2021 | Ongoing
1.3.3 | Randstad | Project Sponsor | Assigned | Unknown | Summer 2021 | Ongoing
1.3.4 | ResearchGate | Project Sponsor | Assigned | Unknown | Summer 2021 | Ongoing
1.3.5 | Kolabtree | Project Sponsor | Assigned | Unknown | Summer 2021 | Ongoing
2.0 | Execution Phase
Level 1
2.1 | Primary & Secondary Site Allocation | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.2 | Primary Site - Underground - Excavation | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.3 | Secondary Site - Abandoned Offshore Oil Rig - Refitment | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.4 | OSHA - Occupational Safety & Health Administration | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
2.5 | Alcor - Cryogenic Freezing, Preservation, & Storage | Project Sponsor | Unassigned | Unknown | Summer 2021 | Ongoing
Level 2
2.2.1 | Lockheed Martin - Electrical Engineering | Project Sponsor | Assigned | Unknown | Spring 2022 | Ongoing
2.2.2 | Baldridge & Associates - Structural Engineering | Project Sponsor | Unassigned | Unknown | Spring 2022 | Ongoing
Level 3
2.3.1 | Roto Rooters - Plumbing Company | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
2.3.2 | Ameriquai - Meals Ready To Eat | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
2.3.3 | Blacks Water Conditioning - Water Purification | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.0 | Performance & Monitoring Phase
Level 1
3.1 | Completion of Facilities for Storage | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.2 | International Approval for Scientists to Enter Regions | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.3 | Primary backup of all seedlings of the Doomsday Vault | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.4 | Secondary backup of all seedlings of the Doomsday Vault | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.5 | Record Coordiation of all Sites & Doomsday Vault | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
Level 2
3.2.1 | Biologists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.2.2 | Agronomists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
Level 3
3.3.1 | Botanists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.3.2 | Cytologists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing
3.3.3 | Marine Biologists | Project Sponsor | Unassigned | Unknown | Unknown | Ongoing